## Sheet1
Main Task | Sub-Task | Dates | Days | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Preparation | Finalise project topic with supervisor | 26th Mar - 3rd Apr | 9
| Identify suitable dataset on Tuberculosis | 11th Apr - 24th Apr | 13
| Start background reading on GPR | 11th Apr - 24th Apr | 13
Project Plan | Initial draft of the project plan | 14th Apr - 1st May | 18
| Make ammendments to project plan | 1st May - 20th May | 19
Literature Review | Initial Literature Review Draft (2000 words) | 14th Apr - 1st May | 18
| Ammendments to Literature review draft | 1st May - 10th May | 9
| Complete Literature review for submission | 1st May - 20th May | 19
Analysis | Exploratory data analysis (EDA) of dataset | 20th May - 4th Jun | 16
| Identify features for Tuberculosis progression | 10th Jun - 17th Jun | 8
| Systematically filter vital features | 17th Jun - 28th Jun | 12
| Report the methodology used for filtering | 30th Jun - 10th Jul | 11
Design | Review existing Gaussian Process regression (GPR) kernels | 20th May - 1st Jun | 13
| Develop a custom kernel for Tuberculosis progression | 3rd Jun - 17th Jul | 45
Implementation | Fit the data to the GPR model | 17th Jul - 26th Jul | 10
| Use GPR model to predict Tuberculosis progression | 29th Jul - 31st Jul | 3
| Report the implementation and results of the model | 31st Jul - 7th Aug | 8
Evaluation | Evaluate the GPR model with the custom kernel | 31st Jul - 10th Aug | 8
| Identify the model's limitations and potential improvements | 10th Aug - 17th Aug | 8
Milestones |  |  |  | April Week 4: Milestone 1; May Week 3: Milestone 2; August Week 2: Milestone 3
[7 empty] | Literature review and project plan draft |  |  | Literature review and project plan submission | [10 empty] | Final Project Submission